{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["Arkusz1","Arkusz2","Arkusz3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Arkusz1","index":0,"n_rows":27,"n_cols":12,"rows_kept":27,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
[]
[null,null,"Nazwa i adres Wykonawcy",{"$nulls":6},"miejscowość, data"]
[]
[null,null,"Haromonogram Rzeczowo-Finansowy"]
[]
[]
[null,"Lp.","Zakres rzeczowy","Kwota / zł /","2008 rok / część graficzna /"]
[null,null,null,"Netto","V","VI","VII","VII","IX","X","XI","XII"]
[null,"I","Przełożenie koryta rz. Czarnej w tym:"]
[null,null,"1.wyk. nowego koryta  wraz z ubezpieczeniem L=230 m"]
[null,null,"2.wykonanie w korycie rzeki bystrza/ spad 0,3 m;L=8,0 m/"]
[null,null,"3.wykonanie w korycie rzeki brodu / szer 3,0 m /"]
[null,"II","Zabezpieczenie skarpy w tym:"]
[null,null,"1.wykonanie nasypu dociążającego / 39 502 m3 /"]
[null,null,"2.kotwienie skarpy osuwiska /122 szt. L=9,0 m; śr. 32 mm/"]
[null,"III","Wykonanie rowu odwadniającego wraz z ubezpiecz."]
[null,null,"1.Wyk. rowu odwadniającego wraz z ubezpiecz.L=174 m"]
[null,null,"RAZEM "]
[null,null,"Podatek VAT"]
[null,null,"Ogółem"]
[]
[null,null,"Ogółem netto / zł / Słownie:"]
[null,null,"Podatek VAT / zł / Słownie:"]
[null,null,"Ogółem brutto / zł / Słownie:"]
[]
[{"$nulls":7},"Podpis i pieczątka"]

{"sheet":"Arkusz2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"Arkusz3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}